## DO NOT DELETE
This template is an exclusive property of Mapua-Malayan Digital College and is protected under Republic Act No. 8293, also known as the Intellectual Property Code of the Philippines (IP Code). It is provided solely for educational purposes within this course. Students may use this template to complete their tasks but may not modify, distribute, sell, upload, or claim ownership of the template itself. Such actions constitute copyright infringement under Sections 172, 177, and 216 of the IP Code and may result in legal consequences. Unauthorized use beyond this course may result in legal or academic consequences. Additionally, students must comply with the Mapua-Malayan Digital College Student Handbook, particularly with the following provisions: * Offenses Related to MMDC IT: - Section 6.2 – Unauthorized copying of files - Section 6.8 – Extraction of protected, copyrighted, and/or confidential information by electronic means using MMDC IT infrastructure * Offenses Related to MMDC Admin, IT, and Operations: - Section 4.5 – Unauthorized collection or extraction of money, checks, or other instruments of monetary equivalent in connection with matters pertaining to MMDC Violations of these policies may result in disciplinary actions ranging from suspension to dismissal, in accordance with the Student Handbook. For permissions or inquiries, please contact MMDC-ISD at isd@mmdc.mcl.edu.ph.

## Effort Estimation
MO-IT101 - Computer Programming 1
Effort Estimation
GUIDE QUESTION | TASK | RESPONSE
What are the main tasks you need to do? (Insert additional rows if you have more than 10 tasks) | 1 | Analyze payroll system requirements
| 2 | Identify user roles and access levels
| 3 | Design use case diagram
| 4 | Create system wireframes
| 5 | Define employee information structure
| 6 | Design hours worked computation logic
| 7 | Design gross salary computation logic
| 8 | Define deduction rules and net salary computation
| 9 | Design payroll report format
| 10 | Review, testing, and revisions
What do you need to know to accomplish these tasks? (Insert additional rows if you have more than 10 tasks) | 1 | Basic system analysis and requirement gathering
| 2 | Understanding of payroll processes and role-based access
| 3 | UML use case diagram concepts
| 4 | Wireframing principles and UI flow
| 5 | Employee data fields and validation basics
| 6 | Time tracking and hours computation logic
| 7 | Salary computation formulas
| 8 | Payroll deductions and net pay calculation
| 9 | Report layout and data presentation
| 10 | Basic testing, documentation review, and revision skills
What additional help do you think you need to be able to do each task? (Insert additional rows if you have more than 10 tasks) | 1 | Course module readings and sample payroll systems
| 2 | Previous lab activities and class discussions
| 3 | UML diagram examples from lectures
| 4 | Wireframe samples and Canva/Figma references
| 5 | MotorPH case details provided in class
| 6 | Payroll computation examples
| 7 | Salary computation formulas from lessons
| 8 | Deduction rules discussed in course materials
| 9 | Sample payroll report formats
| 10 | Coach/Mentor feedback, rubric, and peer review
Given the nature of the task, the knowledge you need, and any additional help you need, how long do you think it would it take you (in hours) to finish each task? (Insert additional rows if you have more than 10 tasks) | 1 | Analyze payroll system requirements – 3 hours
| 2 | Identify user roles and access levels – 2 hours
| 3 | Design use case diagram – 3 hours
| 4 | Create system wireframes – 4 hours
| 5 | Define employee information structure – 2 hours
| 6 | Design hours worked computation logic – 2 hours
| 7 | Design gross salary computation logic – 2 hours
| 8 | Define deduction rules and net salary computation – 2 hours
| 9 | Design payroll report format – 2 hours
| 10 | Review, testing, and revisions – 3 hours
In this course, you are expected to dedicate 7.5 hours per week. Based on the total number of hours you estimated, how many weeks will you need to finish your outputs? | Total Estimated Hours: 25 hours Weekly Expected Time: 7.5 hours Estimated Duration: ~3.5 weeks (rounded to 4 weeks)

## Project Plan Guide
MO-IT101 - Computer Programming 1
Project Plan Guide
Use the guide below to help you fill out this template
1 | Begin by filling out the general information section above.
2 | TASK # - Use whole numbers to specify main tasks (e.g., 1,2,3). If the task is considered a sub-task, advance the numbering using decimal points to still identify what the main task is (e.g., 1.1, 1.2, 1.3).
3 | TASK - Describe the task. Start tasks with verbs/action words to add specificity, e.g., List requirements instead of simply Requirements.
4 | DEPENDENCY - Identify the task which cannot be started unless a previous task has been completed. Leave this blank if there is no dependency.
5 | OWNER - Identify the person responsible for completing the task.
6 | START DATE & END DATE - Identify the planned start and end dates per task. The main task's start and end-date should be the start date of the first sub-task and the end date of the last sub-task. The last end date in your project plan should be within the submission dates indicated in your syllabus.
7 | STATUS - By default, all tasks start with a Not Started status. Change the status to In Progress if it's already being worked on and Completed once the task is done.
8 | ACTUAL START & END DATE - Specify the actual start and end dates per task. This allows you to identify whether you were able to adhere to your initial timelines and if you will be able to complete the rest of your tasks on time. If you see that you don't have sufficient time, you need to work with your team to decide on alternatives or adjustments.
9 | NOTES - Indicate any notes or reminders you may have for each task.

## Project Plan
MO-IT101 - Computer Programming 1
Project Plan
TASK # | TASK | DEPENDENCY | OWNER | START DATE | END DATE | STATUS | ACTUAL START DATE | ACTUAL END DATE | NOTES
1 | Phase 1: Requirements & Design | - | Group 28 | Week 4 | Week 4 | Completed | 2026-01-26 | 2026-02-01 | Finalized use case diagrams and wireframes.
2 | Setup GitHub & IDE Environment | 1 | Group 28 | Week 5 | Week 5 | Completed | 2026-02-01 | 2026-02-08 | Repo created, NetBeans project initialized.
3 | Develop PayrollCalculator Class | 2 | Group 28 | Week 6 | Week 6 | Completed | 2026-02-09 | 2026-02-15 | Built Gross, Deductions, and Net formulas.
4 | Develop MotorPH_App Main Logic | 3 | Group 28 | Week 7 | Week 7 | Completed | 2026-03-03 | 2026-03-05 | Integrated calculator class with main method
5 | Implement Professor's GC Rulings | 4 | Group 28 | Week 8 | Week 8 | Completed | 2026-03-06 | 2026-03-07 | Added 10-min grace period, lunch boundary fix, and 2nd cutoff rul
6 | Testing, Debugging & Submission | 5 | Group 28 | Week 9 | Week 10 | Completed | 2026-03-07 | 2026-03-07 | Fixed syntax errors, achieved BUILD SUCCESSFUL, pushed to GitHub.
7 |  | 6 | Group 28 | Week 11 | Week 11 | Not Started
8 | [5 empty] | Not Started
9 | [5 empty] | Not Started
10 | [5 empty] | Not Started
11 | [5 empty] | Not Started
12 | [5 empty] | Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started